# ACSI Continuous School Improvement Plan Samples

| School Improvement #1: The board is currently only trained in the founding philosophy documents on an ad hoc basis without any scheduled process in place. A new process will be developed and more comprehensive training documents developed. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal: To ensure board familiarity with the school’s key philosophical principles over time |  |  |  |  |
| Total Time: 5 years Date Begun: ___________________ Date Finished: ________________ |  |  |  |  |
| Actions | Who is Responsible? | Resources Needed | Time-Line | Action Completion Monitoring |
| 1. Gather samples of approaches used by other, similar, accredited schools | Board Chairman | - List of key accredited schools from ACSI | 6 months | A sample questionnaire will be generated and sent out. |
| 2. Review the approaches used by others and generate an applicable approach for use at CCCS | Board members and school CEO | - Time scheduled in the board schedule | 6 months | A recommendation will be made by the board for a model (or the development of a model) |
| 3. Implement the pilot approach / schedule for several cycles of new board members | Board Chairman | - Special scheduled board training sessions - training resources for board members | 3 years | Personal discussion with board members 1 year after coming on the board to assess familiarity with philosophical documents |
| 4. Revise the process and solidify the protocol in the board policies | School CEO | - Dedicated day for revision of the process - Secretarial time for updating the process & inclusion in the board policy manual | 1 year | Updated board manual that reflects training component and schedule. |
| 5. Implement the new process | Board Chairman School CEO Board members | - new policy document - training protocol | 3 months | Training time during summer board retreat |
| 6. Poll the board members on the training process – awareness of school mission and philosophy | Board Chairman | - evaluation rubric | 1 month | Completion of training evaluation Review of the training time during the board retreat |
| 7. Evaluate the effectiveness of the training | Board Chairman School CEO | - Completed evaluations | 1 month | Adjust training program to reflect data gathered from the board evaluations |

| School Improvement Goal #2: Creation of a student mentoring program that connects high school students with key faculty in a relationally based, supportive environment while providing strong biblical accountability and life-choices goals. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome: A program that connects all students with a mentor teacher |  |  |  |  | Student Benefit: Connection with a staff adult that knows their needs and is available for input, encouragement, and guidance. |  |  |  |
| Project duration: 6 Years |  |  | Begin Date: June 2002 |  |  | Completion Date: June 2008 |  |  |
| Timeline | Person(s) Responsible | Strategy |  | Resources Needed |  |  | Staff Development | Completion Evidence |
| Year 1 | - Superintendent - Mentoring committee | - Poll the students for identified needs and issues facing HS students today - Discussion with developmental professionals on approaches to mentoring |  | - Survey for students - Funding for survey assessment |  |  | none | Data on student issues Input from the professional community |
| Year 2 | - Mentoring committee | - Research programs and/or schools with mentoring programs in place. |  | - Travel funds for visiting programs and/or schools |  |  | none | Synthesized report on current program application |
| Year 3 | - Mentoring Committee | - Create a proposal for a mentoring program |  | - Flex time for mentoring team meeting |  |  | none | Draft proposal |
| Year 4 | - Board / admin | - Review the proposal by the board and administrative team |  |  |  |  |  | Edited version of proposal |
|  | - Mentoring committee | - Recommendation for implementation of the proposed program |  | - Final copy of proposal - In-service day for presentation |  |  | Orientation on mentoring programs and goals |  |
| Year 5 | - Admin and Mentoring committee | - Finalize the mentoring program details for implementation in the fall |  | - Stipend for summer work |  |  |  | Finalized program guide |
| Year 6 | - Mentoring committee | - Generate a student mentoring handbook - Generate a mentor’s handbook - Generate a mentoring schedule |  | - stipend for summer work |  |  |  | Handbooks |

| Improvement Goal #1: To create a board policy and resulting protocol that will balance the input of newly inculcated families with the historical foundations of the school in any review and revision process of the key philosophic ideas and documents – mission, vision, school goals. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome: A well-balanced review and revision policy and process that serves parental input of new families and long term families |  |  |  |  |  | Benefit to Students or Learning Environment: Security and continuity of school mission, resulting in a consistently applied school program and outcomes |  |  |  |
| Project duration: 3 Years |  |  |  | Begin Date: June 1, 2001 |  |  | Completion Date: July 30, 2004 |  |  |
| Timeline | Person Responsible | Research | Strategy |  | Resources Needed |  |  | Staff Development | Completion Evidence |
| Year 1 | - Board chair - Superintendent | - Current trends in stakeholder orientation to school mission - Obtain samples of revision policies from other schools | - Review the current policy on revision of mission and vision statements - compare current policy to similar schools of age and mission |  | - Board policy document - Samples of revision policies from other schools |  |  | none | Selection of samples from other schools. |
| Year 2 | - School board |  | - Recommend potential rewrite of the current policies for revision. - Review weight of input from board members |  | - Policy document |  |  | Board trainer |  |
| Year 3 | - School board |  | - Generate an updated protocol that reviews the mission |  | - Funding for reprinting the board policy manual |  |  | Orientation of board | Next review of mission and vision |
|  |  |  | - Balance the weight of input between board members with history and those new to the process |  |  |  |  | Application of new board protocol |  |

| Ongoing School Improvement #2: Creation of a student mentoring program that connects high school students with key faculty in a relationally based, supportive environment while providing strong biblical accountability and life-choices goals. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Begin: June 2002 |  |  | Projected Completion: June 2005 |  | Research: Student mentoring; school programs |  |  |
| Student or Learning Benefit: Connection of students with a staff adult on campus that knows their needs and is available for input, encouragement, and guidance |  |  |  |  |  |  |  |
| Timeline | Projected Costs | Action Items |  | Accountability |  | Resources Needed | School Outcomes |
| Year 1 Fall | $2000.00 | - Poll the students for identified needs and issues facing HS students today |  | - Superintendent |  | - Survey for students - Funding for survey assessment | Data on student issues |
|  |  | - Discussion with developmental professionals on approaches to mentoring |  | - Mentoring committee |  |  | Input from the professional community |
| Spring | $3500.00 | - Research programs and/or schools with mentoring programs in place. |  | - Mentoring committee |  | - Travel funds for visiting programs and/or schools | Synthesized report on current program application |
| Year 2 - Fall |  | - Create a proposal for a mentoring program |  | - Mentoring Committee |  | - Flex time for mentoring team meeting | Draft proposal |
| Spring | $500.00 | - Review the proposal by the board and administrative team |  | - Board / admin - Mentoring committee |  | - Final copy of proposal - In-service day for presentation | Edited version of proposal |
| Year 3 Summer | $750.00 | - Finalize the mentoring program details for implementation in the fall |  | - Admin and Mentoring committee |  | - Stipend for summer work | Finalized program guide |
| Fall | $5.00 / student | - Generate a student mentoring handbook - Generate a mentor’s handbook - Generate a mentoring schedule |  | - Mentoring committee |  | - stipend for summer work | Handbooks Mentoring guide matrix Students assigned to mentors |